{"text_format":"3","workbook":"xls","n_sheets":1,"sheets":["Sheet1"],"read":"whole","date_system":"1900","formulas":"cached_only"}

{"sheet":"Sheet1","index":0,"n_rows":13,"n_cols":5,"rows_kept":13,"merged":[[0,0,0,1],[2,0,2,4]],"flags":["formulas_cached_only"]}
["附件2"]
[]
["“证照分离”改革试点工作任务推进表"]
["序号","重点任务","牵头部门","配合部门","完成时限"]
[1,"制定辽阳高新区管委会改革工作方案。","辽阳高新区管委会、市编委办","市政府法制办、涉及改革事项的有关部门","3月10日前报省审改办备案，3月25日前以市政府文件向社会公布"]
[2,"根据省直相关部门针对具体改革事项统一制定的标准文书、程序和举措，推进各改革事项落地实施；对于国家、省级改革权限的事项，要积极与上级部门对接，做好具体承接、配合和落实工作。","辽阳高新区管委会、市编委办","市工商局、市政府法制办、\n涉及改革事项的有关部门","按省统一部署\n3月20日前"]
[3,"通过广播、电视等媒体，依托门户网站、办事大厅等平台公布改革事项、解读改革政策、宣传改革举措。","辽阳高新区管委会、市编委办、市工商局","涉及改革事项的有关部门","3月30日前"]
[4,"全面组织实施。","辽阳高新区管委会、市编委办、市工商局","涉及改革事项的有关部门","3月30日至12月21日"]
[5,"在政府网站及政务服务中心公开行政审批事项、办事指南、中介服务事项清单及审批受理、办理进展情况和结果等行政审批信息。","辽阳高新区管委会","市编委办、市营商局","4月30日前"]
[6,"推进实施“双随机、一公开”监管。","市工商局、辽阳高新区管委会","涉及改革事项的有关部门","6月30日前"]
[7,"完善辽阳高新区管委会事中事后的监管平台功能，推进企业注册、行政许可、信用管理监管执法等信息的共享，建立健全信用联合激励和失信联合惩戒制度。","辽阳高新区管委会","市发改委、市工商局、市营商局","6月30日前"]
[8,"力争提前完成接入国家和省、市政务信息共享交换平台的建设。","市发改委、市政府办","辽阳高新区管委会、市工商局、市营商局","根据国家、省、市平台建设进度"]
[9,"开展“证照分离”改革试点督促检查和成效评估。","辽阳高新区管委会、市编委办、市工商局、市政府法制办","涉及改革事项的有关部门","8月31日前"]